## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Janhavi Rajurkar | 2026-02-09 | Unused imports not detected correctly for certain Python files. | Sprint 1 | Self | Logical | Improved AST traversal logic to correctly identify unused imports. | 2026-02-10 | Closed | Issue resolved and validated with sample programs.
2 | Janhavi Rajurkar | 2026-02-11 | PEP8 style violations not highlighted consistently in output. | Sprint 1 | Self | Standards | Integrated stricter PEP8 checks and improved formatting rules. | 2026-02-13 | Closed | Style detection accuracy improved to 95%
3 | Janhavi Rajurkar | 2026-02-17 | False positive: Flagging valid function as syntax errors. | Sprint 2 | Self | Logical | Updating AST parser to correctly handle Python 3.6+ type annotations. | 2026-02-18 | Closed | Parser now correctly validates modern Python syntax.
4 | Janhavi Rajurkar | 2026-02-24 | Optimization suggestions sometimes irrelevant to code context. | Sprint 3 | Self | Logical | Refined prompts to provide contextual suggestions. | 2026-02-26 | Closed | Suggestions now highly relevant and specific.
5 | Janhavi Rajurkar | 2026-03-05 | Long code samples cause performance degradation in style checker. | Sprint 4 | Self | Maintainability | Optimized PEP8 checking algorithm. | 2026-03-06 | Closed | Processing time reduced for large files.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others